## Sheet1
Task | Start Date | End Date | Duration | Dependency
Project Planning | 01-Sep | 07-Sep | 1 Week | -
Requirement Gathering | 08-Sep | 14-Sep | 1 Week | Project Planning
UI/UX Design | 15-Sep | 05-Oct | 3 Weeks | Requirement Gathering
Low Fidelity Prototyping | 15-Sep | 21-Sep | 1 Week | UI/UX Design
High Fidelity Prototyping | 22-Sep | 05-Oct | 2 Weeks | Low Fidelity Prototyping
System Development | 06-Oct | 27-Oct | 3 Weeks | UI/UX Design
Backend Development | 06-Oct | 19-Oct | 2 Weeks | System Development
Frontend Development | 20-Oct | 27-Oct | 1 Week | Backend Development
Testing | 28-Oct | 10-Nov | 2 Weeks | System Development
Unit Testing | 28-Oct | 03-Nov | 1 Week | Testing
Integration Testing | 04-Nov | 07-Nov | 1 Week | Unit Testing
User Acceptance Testing | 08-Nov | 10-Nov | 3 Days | Integration Testing
Deployment & Review | 11-Nov | 14-Nov | 4 Days | Testing